## Sheet1
Example project plan
|  |  | W/C 16/11 |  |  |  |  | W/C 23/11 |  |  |  |  | W/C 30/11 |  |  |  |  | W/C 07/12 |  |  |  |  | W/C 14/12 |  |  |  |  | W/C 21/12 |  |  |  |  | W/C 28/12 |  |  |  |  | W/C 04/01/16 |  |  |  |  | W/C 11/01/16 |  |  |  |  | W/C 18/01/16 |  |  |  |  | W/C 25/01/16 |  |  |  |  | W/C 01/02/16 |  |  |  |  | W/C 08/02/16 |  |  |  |  | W/C 15/02/16 |  |  |  |  | W/C 22/02/16 |  |  |  |  | W/C 29/02/16
Task | Who | Status | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Functional Requirements
Requirements gathering | Worldspan | Complete
Defining functional requirements | Worldspan | Complete
ESSO review and feedback | ESSO | Complete
ESSO approval | ESSO | Received
Site Structure
Define site structure identify required views and user work flow | Worldspan | WIP
Create wireframes of required views for desktop and mobile devices | Worldspan | WIP
ESSO review and feedback | ESSO
ESSO approval | ESSO
Software Implementation
Server environment and application set up | Worldspan | Complete
Application modelling - Development of required applications models | Worldspan | WIP
CMS implementation - Development of application CMS | Worldspan | WIP
Design and Development of User Interface
Static design of UI | Worldspan
ESSO review and feedback | ESSO
ESSO approval | ESSO
HTML and CSS template coding | Worldspan
Application integration | Worldspan
Paypal integration | Worldspan
Deploy to preview | Worldspan
Population | Worldspan
Browser testing and debugging | Worldspan
Application testing and bebugging | Worldspan
Usability acceptance testing | ESSO
ESSO review and feedback | ESSO
ESSO approval | ESSO
CMS training | Worldspan
Website depolyment - Go live | Worldspan