## Condensed Schedule
Date / Week Number
Activity | Lead | 2016-01-11 | 2016-01-18 | 2016-01-25 | 2016-02-01 | 2016-02-08 | 2016-02-15 | 2016-02-22 | 2016-02-29 | 2016-03-07 | 2016-03-14 | 2016-03-21 | 2016-03-28 | 2016-04-04 | 2016-04-11 | 2016-04-18
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
WEBSITE
Image Collection & Creation | KQ & FN | bar: 1 to 5
Website Build / Amends | 3 Internet | bar: 3 to 14
Website Structure Finalised | All | bar: 1 to 2
Content Topics & Format | NS & AD | bar: 1 to 2
Content Guideline Principles | KQ | bar: 1 to 2
Content Creation / Upload | All | bar: 4 to 14
Content guidelines issued to contributors | FN | bar: 2
Start working on new videos, infographics, case studies | FN & KQ | bar: 3 to 13
Deadline for text only content | All | bar: 4 to 5
Basic site ready for review | 3 Internet | bar: 7 to 8
Internal Review | NS/AD/FN/KQ | bar: 8 to 9; 13
Testing & Research | All / KQ | bar: 10 to 12
SOCIAL MEDIA
Content Scheduling | FN | bar: 4 to 13
HANDOVER
Document Library | KQ & FN | bar: 14 to 15
Upskilling | KQ & FN | bar: 14 to 15
Doc Transfer | KQ & FN | bar: 14 to 15
New Meeting Approach | All | bar: 6 to 13
Note on I18: Start to post daily content