## Long Term Plan
IBO 2017 Project Plan
| Who? | Deadline? | Complete? | Notes
Programme
Decide programme for opening ceremony | Isabel/Norma | September 2016 | Yes
Decide programme for cultural evening | Isabel | February 2017 | Yes
Decide programme for award dinner | Isabel | September 2016 | Yes
Finalise social programme | Isabel/Becky | February 2017 | Yes
Invite VIPs | Isabel/Norma | March 2017 | Yes
Finalise programme timings | Isabel/Andy | October 2016 | Yes | Adult programme may change for Frid/Sat
Publish updated programme on website | Isabel | October 2016 | Yes
Source entertainment for opening ceremony | Isabel/Kevin/Marissa/Andy/Norma | November 2016 | Yes | Potential to use Warwick societies
Source entertainment for cultural evening | Isabel/Kevin/Charlotte/Andy | November 2016 | Yes | Potential to use Warwick societies
Book excursions/transport | Isabel | January 2017 | Yes - provisional | Will finalise once numbers are confirmed
Finalise VIP attendance |  | February 2017 | Yes
Final theory questions | Andy/Matt/Josh |  | Yes
Final practical questions | Andy/Kevin/Leanne |  | Yes
Sub-group | Andy | October 2016 | Yes | Need to book different room
UKBC and other volunteers | Andy/Rachel | February |  | Need to confirm roles and any need for accommodation
Education session | Andy/Mary | June 2017
Exam system | Daniel/Jonas/Andy | Available from October 2016 | Yes | Further development from October
Russian translation of theory papers | Michael | From October | Yes
Russian translation of practical papers | Warwick SLS staff? |  | Yes
Send speaker briefs/guidelines for speeches | Isabel | May 2017 |  | Aiming to keep speeches brief!
Yearbook
Volunteers
Add volunteer information to website | Isabel | September 2016 | Yes
Use contacts to source potential volunteers | All | From September 2016 | Yes
Create Volunteer Registration Form | Isabel | September 2016 | Yes
Volunteer Information Pack | Isabel | September 2016 | Yes
Open volunter registration | Isabel | October 2016 | Yes
Start volunteer master | Isabel | October 2016 | Yes
Volunteer programme/timetable | Isabel/Becky/Norma | March 2017 | Yes
Close volunteer registration | Isabel | End January 2017 | Yes
Allocate volunteer tasks | Becky | March 2017
Volunteer Training |  | April 2017? |  | No budget for this at the moment
Volunteer Information Pack | Isabel/Becky | April 2017?
Onsite volunteer training |  | July 2017
Volunteer DBS checks | Rachel | ?
Misc.
Gifts/Merchandise | Isabel/Norma | May 2017 | Yes
Microscopes | Kevin/Leanne/Rachel | May 2017 | Yes | No budget for this at the moment
Printed programme - liaise with Nick | Isabel/Designer Nick | March 2017 | Yes
Branding/banners | Isabel/Designer Nick | March 2017 | Yes
Medals | Isabel/Norma | March 2017 | Yes
Warwick
Finalise Room requirements | Isabel/Jane | October 2016 | Yes
Update booking contract | Isabel/Jane | October 2016 (Jan 2016 for update on bedrooms) | Yes
Labs/Equipment for practicals | Kevin/Leanne |  | Yes
Second site visit | Isabel/Rachel/Jane | February 2017 | Yes
Update booking contract with numbers | Isabel/Jane | March 2017 | Yes
Menus | Isabel/Jane | End May 2017 | Yes
AV requirements | Isabel/Jane | End May 2017 | Yes
Arrange minibus shuttles | Isabel | May 2017 | Yes | (Can book earlier - will need to finalise details later)
Send lists to IT | Isabel | End May 2017 | Yes
Registration
Registration information to website | Isabel | September 2016 | Yes
Draft invitation letters | Isabel | October | Yes
Finalise Registration Fees | Rachel/Andy | End October 2016
Contact Yvonne for safeguarding disclaimer wording | Isabel | October | Yes
Send Invitation Letters | Isabel | Mid November | Yes
Collate expression of interest | Isabel | End January 2016 | Yes
Registration form | Roel | End January 2017 | Yes
Open regsitration |  | February 2017 | Yes
Start arrival master | Isabel | January 2017 | Yes
Collate registrant details for IT | Isabel | May 2017 | Yes
Collate adult details for IT | Isabel | May 2017 | Yes
Sponsorship
Sponsorship prospectus/brochure | Jon Day/Rachel/Isabel | September 2016 | Yes
Approach sponsors for microscope |  |  | Yes
Approach sponsors for gifts | Isabel/Norma/Rachel | Ongoing | Yes
Media
Populate website | Isabel | September 2016 | Yes
Social Media Calendar | Isabel | September 2016 | Yes
Update emails to registrants | Isabel | From March/April 2017?
Daily News Plans |  | June 2017
FAQ page | Isabel | Ongoing | Yes
Move flags to Warwick | Isabel | April | Yes
Purchase additional flag poles and flags | Isabel | April | Yes
Other
Event Insurance | Isabel | October 2016 | Yes
Risk Register | Isabel | October 2016 | Yes
Public Liability Insurance | Isabel/Rachel | December 2016 | Yes
Safeguarding Policy | Rachel
Risk Assessment
Behaviour Policy | Isabel/Rachel | October 2016 | Yes
Onsite
Registration desk plan | Isabel | February 2017
Bag packing | Volunteers | July 2017
Volunteer briefing | Becky Peel/Norma | July 2017
Volunteer tour | Becky Peel? | July 2017
Set up practical exams | Volunteers | July 2017
Take student quotes for report | Volunteers | July 2017
Staff task-list/briefing document | Isabel | June 2017
Post-Event
Post-event report | Isabel | August 2017

## May to July
IBO 2017 May to July
Programme | Date | Tasked | Status | Notes
Finalise Programme Timings | May | Isabel | Done
Welcome Board |  |  | Done
Contact Coventry & Birmingham Airport | May | Isabel/Norma | Done
Agenda for AGM | July | Poon?
Email delegations re. Education Session | First week July | Isabel | Done
Agenda for Education Session | June | Andy?
Social Programme
Finalise Opening Ceremony Entertainment Bookings | Early June | Rachel | Done
Create running order & circulate to acts | June | Rachel | Done
Finalise Guest list for Opening Ceremony | June | Isabel | Done
Final Details Email to Opening Ceremony Guests | July | Isabel | Done
Seating plan Opening Ceremony | July | Isabel/Karen | Done
Reserved Signs | July | Isabel/Karen | Done
Table plan Awards Dinner | July | Isabel | Done
Opening Ceremony Slideshow | June | Rachel/Norma/Isabel | In progress
Opening Ceremony playlist | July | Rachel | Done
Buy extra flags/poles | June | Rachel | Done
Rehearsal schedule | July | Rachel | Done
Confirm Warwick Castle Numbers & pay | 1st week July | Isabel | Done
Confirm Boat Tour Numbers | June | Isabel | Done
Confirm Cathedral Numbers | June | Isabel | Done
Confirm Transport Museum Numbers | June | Isabel | Done
Confirm Johnson's numbers | June | Isabel | Done
Final Email to Zombie Science | July | Isabel | Done
Final Email to Simon Watt | July | Isabel | Done
Final Email to Science Ceilidh | July | Isabel | Done
Music for Awards Dinner | June | Isabel & Jane | Done | Jane approaching DJ
Ideas for ice breakers | June | Volunteers | Done | whatsapp picture idea
Create Cultural Night Programme - printed? | June | Isabel | Done
Science Buskers | June | Rachel | Done | David Urry
Handing out of medals? | June | Isabel/Rachel/Norma | Done | Jean/Mark/Kevin/Leanne/Maggy/Norma
DJ for Cultural Night | June | Isabel & Jane | Done | Jane approaching DJ
Email ice cream man | June | Isabel | Done
Create ice cream vouchers | July | Karen | Done
Exhibition
Confirm with exhibitors | End June | Isabel | Done
Send briefs to exhibitors | July | Isabel | Done
Final Email to exhibitors - inc. delivery information | July | Isabel | Done
Finalise RSB staff attendance | End June | Isabel/Raghav/Amanda | Done
Exams
Finalise Practical Venues | June | Branagh | Done
Book practicals transport | June | Branagh | Done
Final upload of theory questions to system | June | Matt/Josh | Done
Practicals - large scale testing | May | Branagh/Kevin/Leanne | Done
Acquire microscopes | May/June | Anyone! | Done | Wooooooooooo!!!!!
Theory paper instructions | June | Isabel? Matt/Josh? | Done | Printed?
Practical day timetable | June | Branagh | Done
Theory day timetable | June | Matt/Josh/Branagh | Done
Venue
Meeting with Jane | June | Isabel & Rachel | Done
Send final numbers to Jane | June | Isabel | Done
Confirm menus with Jane | June | Isabel | Done
Confirm AV requirements with Jane | June | Isabel | Done
Final confirmation of rooms/spaces | June | Isabel | Done
Confirm room setup | July | Isabel | Done
Risk Assessment | June | Isabel & Rachel | Done
Book poster boards | June | Isabel | Done
Send dietary requirements to Jane | June | Isabel | Done
Send accessibility requirements to Jane | June | Isabel | Done
Collate attendees/volunteers/organisers into one list | June | Isabel | Done
Send attendee list to IT/Branagh | June | Isabel | Done
Warwick Room Allocations |  |  | Done
Create slide for screen | July | Rachel | Done
Minibus shuttles | May | Branagh | Done
Awards Dinner guest list | June | Isabel | Done
Buy mini flags for table centrepieces | June | Karen | Done
Jury room floor plan | June | Isabel | Done
Find space for GE healthcare workshop | June | Isabel/Jane | Done
Find space for lab familiarisation | June | Isabel/Jane | Done
Budget
Update budget | Ongoing | Isabel | Ongoing
Update budget with final costs | July | Isabel/Rachel
VIPs & Speakers
Create formal invitation for Opening Ceremony | June | Karen | Done
Confirm room for VIPs | June | Isabel | Done
Draft speaker briefs and send (Opening Ceremony) | July | Isabel | Done
Draft speaker briefs and send (Awards Dinner) | July | Isabel | Done
Request speaker presentations | July | Isabel | Done | Will there be any?
Final information email to speakers (timings, AV, accommodation, map) | July | Isabel | Done
Send thank you letters & claim forms | August | Isabel
Registration
Chase un-registered teams | May | Isabel | Done
Send invoices | May | Isabel | Ongoing
Chase payments | May/June | Isabel | Ongoing
Collate attendee list | June | Isabel | Done
Badges - Identilam | June | Isabel | Done
Printed Programme
Draft Programme Outline | May | Isabel / Rachel | Done
Draft Programme content | June | Rachel/Karen/Isabel | Done
Get adverts & logos from sponsors | June | Isabel | Done
Send content to Nick | June | Rachel | Done
Proofread | June | All | Done
Send to printers | June | Isabel | Done
Yearbook | July | Karen/Isabel | Done
Volunteers
Send update to volunteers | June | Becky | Done
Allocate team guides | June | Becky | Done
Create volunteer task list | June | Isabel | Done
Allocate volunteer tasks | June | Becky/Isabel
Arrange date for senior guide training | May | Becky | Done
Draft programme for senior guide training | June | Rachel | Done
Draft programme for training | June | Rachel | Done
Final information email for volunteers - confirm timings | July | Becky | Done
Volunteer DBS checks | June | Rachel | Ongoing
Create registration rota | July | Isabel
Misc.
Receive artwork from Archer | May/June | Isabel | Done
Approve Artwork | June | Isabel | Done
Confirm t-shirt sizes with Archer | June | Isabel | Done
Liaise with Nick re. design of banners | June | Isabel/Rachel | Done
Order banners | June | Isabel | Done
Send to print | June | Isabel | Done
Badges | June | Isabel | Done
Check progress of medals | June | Isabel | Done
Create Certificates of Merit | June | Isabel | Done
Hay Bales | June | Rachel | Done
Cadburys | June | Norma/David | Done
Media
Hand over social media to Philippa | July | Isabel | Done
Chase Royal Comm for poster | May | Isabel | Done
Check Jon Day's requirements | June |  | Done
Pre-Event
Confirm staff to attend | July | Isabel | Done
Book materials | July | Karen | Done
Book cameras/photographer | July | Isabel/Karen | Done | Jon Day & team
Book couriers | July | Isabel/Karen | Done
Prepare signage | July | Isabel/Karen | Done
Pack event materials | July | Isabel/Karen | Done
Print volunteer list | July | Isabel/Karen | Done
Print registration rota | July | Isabel/Karen
Create event whatsapp group | July | Isabel/Karen
Book Christina Gebler a taxi | July | Isabel | Done | Arrives Birmingham 22:15 LH958 from Frankfurt TC Cars on 0121 770 2000
Post Event
Write thank you emails to speakers | August | Isabel
Follow up email to attendees | August | Isabel
Process speaker expense claims | August | Isabel

## Friday 21st July
IBO 2017 - Onsite Friday 21st July
Task | Time | Location | Tasked | Status | Notes
Arrival at Warwick | Morning |  | Rachel, Becky, Isabel
Greet Senior Guides | Morning |  | Becky
Senior Guide Training | Morning - Afternoon |  | Rachel & Becky
Greet all volunteers | Afternoon |  | Isabel
Venue Preparations | Morning |  | Isabel
Site Tour | Evening |  | Becky, Volunteers
Equipment
Volunteer list
Volunteer badges
Banners

## Saturday 22nd July
IBO 2017 - Onsite Saturday 22nd July
Task | Time | Location | Tasked | Status | Notes
Volunteer Training | Morning | Rootes | Rachel, Becky
Bag packing | Afternoon | Rootes | Volunteers
IT Briefing | Afternoon | Rootes | Isabel, Rachel, Sri
Venue briefing | Afternoon |  | Isabel, Rachel, Jane |  | Tuesday??
Pre-prep for Opening Ceremony
Pre-prep for jury room
Equipment
Volunteer Information
Bags/gifts
Printed programmes

## Sunday 23rd July
IBO 2017 - Onsite Sunday 23rd July
Task | Time | Location | Tasked | Status | Notes
Brief day volunteers | 8:30 | Rootes | Senior Guides/Becky
Set up registration | 8:30 | SU | Isabel/Volunteers
Registration desk | All day | SU | Volunteers
Showing delegations to rooms | All day |  | Volunteers
Greeting delegations at station and airport | All day |  | Volunteers, Lesley
Shuttling delegations to campus | All day |  | Volunteers
Set up Butterworth Hall - banners, flowers | Midday | Arts Centre | Volunteers, Karen
Coordinate rehearsals | All day | Arts Centre | Norma & Rachel
Upload slideshow and test | Early afternoon | Arts Centre | Rachel/Tom
Give playlist to AV team | Early afternoon | Arts Centre | Rachel
Check microphone working | Early afternoon | Arts Centre | Rachel/Tom
Check catering ok | Early afternoon | Arts Centre | Isabel/Jane
Set up banners in Butterworth Hall | Early afternoon | Arts Centre | Volunteers/Karen
Set up banners in Gallery | Early afternoon | Arts Centre | Volunteers/Karen
Usher guests to Hall | 15:30 | Arts Centre | Volunteers
Greet VIPs & accompany to holding room | 15:30 | Arts Centre | Norma
Backstage management | From 15:00 | Arts Centre | Rachel
Wing management | 16:00 | Arts Centre | Isabel/Karen
Hand out programmes at door | 15:30 | Arts Centre | Volunteers
Check badges/tickets | 15:30 | Arts Centre | Volunteers
Showing to seats | 15:30 | Arts Centre | Volunteers
Showing to Gallery | 15:30 | Arts Centre | Volunteers
Photo management | 18:30 | Arts Centre | Media volunteers
Equipment
Registration signage
Registration rota
Badges
Bags/gifts
Programme booklets
Banners
Banners for airport/coventry
Flowers
Opening Ceremony programmes
Playlist & slideshow on stick
Flags & flag poles
Cameras
Badge label printer

## Monday 24th July
IBO 2017 - Onsite Monday 24th July
Task | Time | Location | Tasked | Status | Notes
Taking devices | Morning | TBC | Volunteers
Logging devices | Morning | TBC | Volunteers
GE Healthcare sign up
Leading students to Cryfield Pavillion | afternoon |  | Volunteers
Leading Ice breaker activities | afternoon | Cryflield Pavillion | Senior Guides/Becky
Set up for lab fams | Afternoon | TBC | Kevin/Leanne/Branagh
Lab familiarisation | morning | science concourse | Kevin/Leanne/Branagh
Move sponsor banners to jury room | Morning | Rootes | Isabel
Jury room check | Morning | Rootes | Isabel
Check microphone working | Morning | Rootes | Isabel
Assisting with internet access | Morning | Rootes | Volunteers
Chairing jury room | All day | Rootes | Andy/Kevin
Managing Printing | Evening | Rootes | Volunteers
Hand out lab coats to students | morning | science concourse | volunteers
Equipment
Boxes for device storage
List of ice breaker activities
Royal Comm poster
Poster board
Rock

## Tuesday 25th July
IBO 2017 - Onsite Tuesday 25th July
Task | Time | Location | Tasked | Status | Notes
Shuttle to practical tasks | All Day | Various | Johnsons
Brief Lab Assistant | Morning |  | Kevin/Branagh
Set up of practical exams | Morning | Various | Lab Assistants, Kevin, Leanne, Branagh
Coordination of practical tasks | All Day | Various | Lab Assistants, Kevin, Leanne, Branagh
Jury room management | All Day | Rootes | Jury Room Assistants
Chairing Jury Room | All Day | Rootes | Andy
Setup for Zombie Science | Evening | Arts Centre | Isabel
Greet Zombie Man | Evening | Arts Centre | Isabel
Check AV working | Evening | Arts Centre | Isabel
Show students to Arts Centre Theatre | Evening | Arts Centre | Volunteers
Equipment
Coaches
Rock
Buckets/baskets

## Wednesday 26th July
IBO 2017 - Onsite Wednesday 26th
Task | Time | Location | Tasked | Status | Notes
Usher Students to Coaches | 8:00 | Arts Centre | Volunteers
Accompany Students to Warwick
Jury room management | All Day | Rootes | Jury Room Assistants
Chairing Jury Room | All Day | Rootes | Andy
Equipment
Coaches
Coach lists
Warwick tickets

## Thursday 27th July
IBO 2017 - Onsite Thursday 27th July
Task | Time | Location | Tasked | Status | Notes
Usher Students to Theory task venues | 8:00 | Arts Centre | Volunteers
Usher jury to coaches | 8:30 | Rootes | Jury Room Assistants
Accompany jury to Stratford | 8:30 | Rootes | Jury Room Assistants
Brief Day Volunteers | 12:00 | Rootes | Senior volunteers/Becky
Setup of exhibition | 12:00 | Rootes | Day Volunteers/Isabel/Karen
Move sponsor banners to Exhibition | 12:00 | Rootes | Isabel/Karen
Setup of square | 14:00 | Rootes | Day Volunteers/Isabel/Karen
Greet Marching Band | 18:00 | Rootes | Isabel
Brief Science Buskers | 15:30 | Rootes | Isabel
Show students into exhibition | 16:00 | Rootes | Volunteers
Manage PE area | All evening | Rootes | Day Volunteers
Greet Science Ceilidh | 19:00 | Rootes | Isabel
Check AV working | 18:30 | Rootes | Isabel/Karen
Usher Students to Ceilidh | 19:30 | Rootes | Volunteers
Equipment
Coaches
Coach lists
Boat tickets
Exhibition Stands
Hay

## Friday 28th July
IBO 2017 - Onsite Friday 28th July
Task | Time | Location | Tasked | Status | Notes
Usher students to coaches | 8:00 | Arts Centre | Volunteers
Accompany students to Coventry | 8:30 | Arts Centre | Volunteers
Setup of Panorama Suite | 8:30 | Rootes | Karen/Isabel
Check AV working | 8:30 | Rootes | Karen/Isabel
Chair General Assembly | Morning | Rootes | Poon/Andy
Education Session | Afternoon | Rootes | ?
Greet Simon | 18:30 | Rootes | Isabel
Setup of Panorama Suite | 18:00 | Rootes | Isabel
Check AV working | 18:00 | Rootes | Isabel
Usher students to Rootes | 19:00 | Rootes | Volunteers
Equipment
Coaches
Coach lists
Cathedral Tickets
Museum Tickets
AGM agenda
Education Session agenda

## Saturday 29th July
IBO 2017 - Saturday 29th July
Task | Time | Location | Tasked | Status | Notes
Brief Day Volunteers | Morning | Rootes | Senior Guides/Becky/Rachel
Sort medals | Morning | Rootes | Volunteers
Set up of Panorama Suite | Afternoon | Rootes | Volunteers/Karen/Isabel
Check table layout | Afternoon | Rootes | Isabel
Brief medal presenters | Evening | Rootes | Isabel
Greet entertainment
Arrange early departures
Equipment
Medals
Certificates
Seating plan
Speaker briefs
Banners

## Sunday 30th July
IBO 2017 - Sunday 30th
Task | Time | Location | Tasked | Status | Notes
Pack down | Morning |  | All
Shuttles | All Day
Prepare for courier
Equipment